## Sheet1
topic to be covered | expected number of days | start date | end date
Study of KMP algorithm and Rabin Karp algorithm | 7 days | 25-09-2020 | 2020-01-10
implementation of KMP algorithm | 5 to 6 days | 2020-01-10 | 2020-05-10
mid term presentation and documentation | 5 days, on going with previous work | 2020-01-10 | 2020-05-10
implementation of Rabin Karp algorithm | 7 days | 2020-10-10 | 17-10-2020
Study of boyer moore algorithm | 3 days | 18-10-2020 | 21-10-2020
Implementation of boyer moore algorithm | 6 days | 22-10-2020 | 28-10-2020
implementation of self made algorithm | 3 days | 29-10-2020 | 31-10-2020
end term presentation and documentation | 4 days | 31-11-2020 | 3 -11-2020
combining of algorithms in one single code and testing the product | during november